## Slide 1: Barrel KLM Detector Status
All detector panels installed by November 2013
One octant (forward top, 1/16th of BKLM) has been instrumented to read out the RPCs (13 outer layers) and scintillators (2 inner layers).
Dry nitrogen gas continues to flow through the remaining octants’ RPCs; switch to chamber gas awaits imminent delivery of replacement gas-mixer part.
HV energizing and health check of remaining octants’ RPCs after ~2 weeks of chamber-gas flow to flush all RPC volumes.

## Slide 2: BKLM/EKLM Readout Status
150 scintillator-panel readout boards awaiting delivery to Hawaii in early September, then ~3 weeks of testing before shipment to KEK. Funded by U.S. Belle II Project.
HV cables for scintillator-panel MPPCs will be delivered to Hawaii in mid September, then shipped with readout boards to KEK. Funded by U.S. Belle II Project.
Readout optical fibers and fiber trunks will be procured in mid September. Funded by U.S. Belle II Project.
36 concentrator cards to be fabricated and tested by Indiana University then delivered to KEK by January 2016. Funded by Nichi-Bei.

## Slide 3: BKLM-only Readout Status
213 RPC-readout cards to be fabricated and tested by Indiana University then delivered to KEK. Bare cards are in hand but no identified funding source for other parts, assembly, testing, shipping.
Estimated funding shortfall is $215K.
Cosmic-ray tests and debugging of readout electronics chain in progress using the instrumented BKLM octant. Cosmic ray tracks are now seen in the raw hits from this octant.